CONTRACTOR AGREEMENT

Widening of RCC Road from New Custom Gate to Container Yard (Balance portion) Near RoRo Yard

PIPAVAV, INDIA

June-2026 CONFIDENTIAL

Page 1 of 34

# CONTRACT AGREEMENT

THIS AGREEMENT (“Agreement”) is made on the Date xx June 2026 at Port of Pipavav, Rajula

# BY AND BETWEEN:

M/s Gujarat Pipavav Port Limited (GPPL) (CIN L63010GJ1992PLC018106) a company incorporated under The Companies Act, 1956 having registered office at Port of Pipavav, Post Rampara-2, via Rajula District Amreli, Gujarat 365 560 - India and Corporate Office at 301, Trade Centre, Bandra Kurla Complex, Bandra East, Mumbai and registered under number 04-18106 at the Chamber of Commerce (hereinafter called “The Employer”) of the ONE PART.

# AND

………………………………………… [name of the Contractor], a company incorporated under the laws of

……………………. and having its registered office at ………………………………… represented by the

…………………… [Designation of the signing authority], hereinafter referred to as the Contractor, (which expression shall unless repugnant to the context or meaning thereof, include its administrators, successors and permitted assigns) on the OTHER PART,

The Employer and The Contractor hereinafter individually referred to as “Party” and collectively as “Parties”.

WHEREAS the Employer is desirous to engage the Contractor for execution of the Works related to Widening of RCC Road from New Custom Gate to Container Yard (Balance portion) and remedying of any defects at APM Terminals Pipavav” (hereinafter referred “The Works”) to the Contractor.

WHEREAS the Contractor has represented and warranted that it has the relevant and adequate experience, expertise, knowledge, capability and resources to undertake execution, completion and guarantee of works on mutually convenient terms and conditions agreed as follows.

NOW THEREFORE, in consideration of the premises and mutual terms and conditions hereinafter set forth the Parties agree as follows.

- In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to.

- The following documents shall form integral part of this Agreement and for the purpose of interpretation were in event of conflict or inconsistency, the priority of documents from high to low shall be in accordance with following sequence

  - This Contract Agreement

  - The Letter of Award dated

  - The Letter of Tender dated

  - The Appendix to Tender

  - The Addenda Nos. and the clarifications

  - Particular Conditions of Contract comprising

    - Annex A: Form of Parent Company Guarantee

    - Annex B: Form of Tender Security

    - Annex C: Form of Performance Security

    - Annex D: Form of Advance Payment Guarantee

    - Annex E: Form of Dispute Adjudication Board Agreement

    - Annex G: Supplier Code of Conduct

  - General Conditions of Contract

  - Instruction to Tenderer’s

  - The Specification,

  - The Drawings and

  - Bill of Quantities, including Preamble

  - Staffing /Organization chart

  - Method Statement

  - Details of Subcontractors

  - HSSE Plan

  - Project Quality Plan

  - Plant and Equipment

  - APMT's Construction Safety Specification

  - APMT’s Contractor Safety Guidelines & Consequence Management

  - APMT Project HSSE Specifications

  - APMT’s Civil Construction guidelines

  - APMT’s Contract Labour Compliance

  - APMT Guidelines on Corruption and Fraud

  - Maersk's Code of Conduct

- The documents forming part of this agreement are mutually explanatory of one other. In case of ambiguities / discrepancies the same shall be explained and adjusted by the Employer and the Engineer who shall thereon issue instructions to the Contractor in this regard. The Contractor shall accept the instructions of Employer and the Engineer without any protest or demur.

- The Contractors hereby warrants and represents that it shall execute and complete the works and remedy any defects therein in conformity with the provisions of the Contract in consideration of the payments to be made by the Employer to the Contractor as mentioned in the Agreement.

- The Employer hereby warrants and represents to pay the Contractor, in consideration of the execution and completion of the Works and the remedying of defects therein, the Agreement price at the times and in the manner prescribed by the Agreement.

- Before the commencement of work, the Contractor shall prepare & submit the Programme and Quality Control Plan (QCP) to the Employer for approval. These shall be strictly implemented and the cost of monitoring the quality and tests etc shall be fully borne by the contractor and shall deemed to be included in Accepted Contract Amount

- The Accepted Contract Amount agreed by the Parties for the execution and completion of the Works and carrying out other obligations in accordance with terms of the Contract

is INR xxxxxx (insert in Words yyyy). The Parties agree that this Contract is a re- measurable Contract and the Contract Price shall be adjusted in accordance with the Contract.

- The Accepted Contract Amount shall be excluding Goods Service Tax (GST) payable at applicable rates, but including of all taxes, duties, levies, Labour & bocw cess, TCS, Import duty, material Royalties, transportation, inspection & certification charges, OR any other state OR corporation tax OR applicable under any rules / regulations / acts / statutes of the State and Central Government duties.

- The Accepted Contract Amount shall also include expenditure for traffic maintenance to avoid constraints of work, safety, diversion and any precautions required to execute the works and expenditure for liaising/dispute resolve with local authorities/villages.

- Employer shall deduct Gujarat State Turnover Tax on Works Contract Tax, Income Tax and any other taxes as per norms of Government of Gujarat & Government of India if applicable.

- Time is the essence of Contract. The Contractor has agreed for timely completion of work and shall deploy sufficient experienced manpower, equipment and machineries to carry out and complete the work as required by the Employer.

The Time of completion of the Works shall be as stated in Appendix to Tender

- The Contractor has verified the site, local working environment and fully conversant with local challenges like compliance of local laws, swift synchronization with local communities, dealing with local administrations etc. The Contractor shall be singularly responsible for execution of all works inside and outside the port boundary by coordinating with the local community and authorities as required for successful completion of the Works.

- All the construction materials, plants, equipment, tools & tackles, manpower, laboratory for test and others such item required/related to this Work for satisfactory completion of the Works shall be provided by the Contractor. The Contractor shall be responsible for supply of any items, materials, equipment etc. in whatever form. Final quoted price by the Contractor shall be deemed to include all the costs required for the satisfactory completion of the contract.

- Contractors shall take all necessary precautions towards safety of human beings, environments, materials, machineries, equipment & assets of GPPL and provide all safety gear including personnel protective equipment (PPE) to his workers, Engineers, staff etc. .as necessary considering the nature of work, at his cost.

# Responsible Procurement

  - The Supplier shall comply with all applicable laws, rules, & regulations, Orders. conventions, or ordinances of the country(ies) where Services/Work is performed or where Goods are produced and/or relate to the provision, licensing, approval or certification of the Services/Goods, including, but not limited to, those relating to occupational health and safety, environmental matters, wages, working hours and conditions of employment, sub-contractor selection discrimination, data protection andprivacy. Further the Supplier shall respect and commit to implementing APMM's Supplier Code of Conduct ("the Code") as amended from time to time and found at; http://www.maersk.com/sustainability/pages/thirdpartycodeofconduct.aspx	or alternatively an internationally recognized standard within the areas of human rights, anticorruption, environment and labour, such as but not limited to United Nations Global Compact (UNGC) and Supplier agrees to accommodate any potential audit pursuant to verification of the same by APMM or Buyer. The Supplier shell require their own suppliers to implement similar rules and as appropriate pass on such requirements to their sub suppliers and so on. The original English version of the Code (as of August 2013) shall prevail in case of any disputes or discussions concerning the content and obligations of either Party. The Supplier warrants that it will register itself in APMM's CSR system (www.MaerskResponsibleProcurement.com) within 14 days after the date of the last signature on the Agreement and shall - if subsequently requested by APMM - provide documentation necessary for APMM to evaluate Supplier's ability to meet the requirements listed in the Code. Should the Supplier be unable to meet the listed requirements, the Supplier will agree to develop and execute an improvement plan.

  - Buyer shall at any time and without notice have the right to appoint at its own cost, charge and expense a well reputed third-party auditor (hereinafter referred to as "Buyer's Auditor") to audit and verify all matters in connection with Supplier's compliance with the previous Clause.

  - Supplier shall cooperate with the Buyer's Auditor and provide access to all relevant sites, people, and interviews with workers and documents. If the Buyer's Auditor uncover(s) any material concern, Supplier shall without any undue delay present Buyer with an improvement plan which shall ensure that all concerns are dealt with and remediated in a manner satisfactory to Buyer. Supplier's repeated violation of the Code/UNGC/International Bill of Human Rights and/or its failure to collaborate with Buyer's Auditor during an audit and/or its failure to· collaborate with Buyer in implementing or developing improvement plans shall be considered a material breach of this Agreement.

  - If Supplier commits any such breach of or fails to observe or perform any material obligation contained in the Code/UNGC/International Bill of Human Rights, and/or any agreed improvement plan, and such breach or failure has not been remedied to the satisfaction of Buyer within twenty-eight (28) days of receipt by the Supplier of a notice from Buyer requiring Supplier to remedy the same (or such longer period as may be specified in the said notice), Buyer shall be entitled to terminate the Contract in accordance with Clause of this agreement-work order.

IN WITHNESS whereof the parties hereto have caused this Agreement to be executed the day and year first before written in accordance with their respective laws.

# SIGNED, SEALED AND DELIVERED

| By the said: The Employer (Gujarat Pipavav Port Limited) | By the said: The Contractor (…………………………………………………………) |
| --- | --- |

| Name: Girish Aggarwal Designation: Managing Director | Name: Designation: |
| --- | --- |
| On behalf of the Employer in the presence of | On behalf of the Contractor in the presence of: |
| Name: Jignesh Lalith Adhyaru Designation: Head of Project | Name: Designation: |
| Gujarat Pipavav Port Limited, Post Rampara No. 2, Via Rajula, District Amreli, Pipavav Port, Gujarat - 365 560 | …………………………………………………………… …………………………………………………………… ………………………………………………………… |

Date: xx.xx.2026 Place: Pipavav Port

PARTICULAR CONDITIONS OF CONTRACT

Particular Conditions of Contract

| 1 | General Provisions |
| --- | --- |
| 1.1.1.9 | Delete Sub-Clause 1.1.1.9 and substitute with the following: ‘Appendix to Tender’ means the pages completed by the Employer and titled as ‘Appendix to Tender’. |
| New definition 1.1.2.11 | “Employer’s Auditor” means an internationally reputed third-party auditor, appointed by the Employer at its own cost, charge and expense. |
| New definition 1.1.2.12 | “Port Authority” means the Port Authority of Gujarat Pipavav Port Limited. |
| 1.1.3.9 | Substitute in Sub-Clause 1.1.3.9, the words “365 days” with “Gregorian Calendar year”. |
| New definition 1.1.3.10 | Insert additional Sub-Clause 1.1.3.10 “Milestone” means the Time for Completion of a Section of the Works, or the occurrence of an identified event. |
| 1.1.4.8 | Substitute the Sub-Clause 1.1.4.8 with the following: “Local Currency” means Indian Rupees (INR). |
| 1.1.6.9 | Delete the Sub-Clause 1.1.6.9 and substitute with the following: “Variation means any changes by the Employer with reference to change in scope of Works, repair methodology & specifications and criteria for the testing & performance of the completed Works specified in the Employer’s Requirements or the Works, which is instructed or approved as a variation under Sub-Clause 13 [Variations and Adjustment].” |
| New definition 1.1.6.10 | “Supplier Code of Conduct” means the Maersk Supplier Code of Conduct as included in Annexure G. |
| New definition 1.1.6.11 | “Port” means the Gujarat Pipavav Port Limited (GPPL). |
| New Sub-Clause 1.15 | Details to be Confidential The Contractor shall treat the details of the Contract as private and confidential, except to the extent necessary to carry out the Contractor's obligations under the Contract or to comply with applicable Laws. The Contractor shall not publish or disclose any particulars of the Works without the previous agreement of the Employer. However, the Contractor shall be permitted to disclose any publicly available information, or information otherwise required to establish its qualifications to compete for other projects. |

| 1.2 | Insert the following sub-paragraphs after sub-paragraph (d): “(e) the word “tender” is synonymous with “bid”, and “tenderer” with “bidder” and the words “tender documents” with “bidding documents”. (f) In these Conditions, provisions including the expression ‘Cost plus reasonable profit’ require this profit to be one-twentieth (5%) of this Cost unless otherwise indicated in the Appendix to Tender” |
| --- | --- |
| 1.6 | Delete the words “annexed to the Particular Conditions” and substitute with “given in Section 8: Contract Forms” at the 3rd line. Replace the word “Employer” with “Contractor” in the last line. |
| 1.7 | Delete the contents of Sub-Clause 1.7 and substitute with the following: “The Employer may assign the whole or any part of the Contract or any benefit or interest in or under the Contract without the prior agreement of the Contractor. |
| 1.11 | Delete the words “, except as necessary for the purposes of the Contract” at the end of paragraph. |
| New clause 1.16 | Add the following new Sub-Clause 1.1: “If the Employer determines that the Contractor and/or any of its personnel, or its agents, or its Subcontractors, sub-consultants, services providers, suppliers and/or their employees has engaged in corrupt, fraudulent, collusive coercive, or obstructive practices, in competing for or in executing the Contract, then the Employer may, after giving 14 days’ notice to the Contractor, terminate the Contractor's employment under the Contract and expel him from the Site, and the provisions of Clause 15 shall apply as if such expulsion had been made under Sub-Clause 15.2. For the purposes of this Sub-Clause, - “corrupt practice” means the offering, receiving, or soliciting, directly or indirectly, of anything of any value to influence the actions of a public official in the selection process or in contract execution - “fraudulent practice” means a misrepresentation or omission of facts in order to influence a selection Process or the execution of a contract; - “collusive practice” means a scheme or arrangement between two or more Tenderers, with or without the knowledge of the Employer, designed to establish prices at artificial, non-competitive levels; - “coercive practice” means harming or threatening to harm, directly or indirectly, person or their property to influence their participation in a procurement process, or affect the execution of a contract. - “obstructive practice” is - deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede an Employer’s investigation into allegations of a corrupt, fraudulent, coercive or |

|  | collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or (ii) acts intended to materially impede the exercise of the Employer’s inspection and audit rights. |
| --- | --- |
| 2 | The Employer |
| 2.1 | Delete the words “plus reasonable profit” from sub-paragraph (b) of third paragraph of Sub-Clause 2.1. |
| 2.2 2.2 A | Add the following at the end of the Sub-Clause 2.2: “For the avoidance of doubt, it is clarified that the Employer, on a best effort basis, will provide reasonable assistance, in the form of writing appropriate letters to the concerned authorities, for obtaining licenses, visas and permits, but without thereby incurring any liability whatsoever towards the Contractor.” Add new Sub-Clauses as follows: 2.2A Permits, Licenses or Approvals – Electrical Works The Contractor shall be solely responsible for obtaining all approvals for the installation of Electrical Works from Chief Electrical Officer, Gujarat Electricity Board, Central Electrical Authority and any other applicable competent authority. The fees for obtaining the approval shall be borne by the Contractor. No claim for any additional time or costs shall be entertained related to delay in sign-off or approval of these works which are entirely the responsibility of the Contractor |
| 2.4 | DELETE this Sub-Clause in its entirety. |
| 3 | The Engineer |
| 3.1 | Delete the last sentence of the 3rd paragraph of Sub-Clause 3.1 and substitute with the following: “The Employer shall promptly inform the Contractor of any change(s) in the authority of the Engineer specified in the Contract or implied from the Contract.” Delete the 4th paragraph of this Sub-Clause “However, whenever the Engineer … … … deemed to have given approval.” Add the following at the end of this Sub-Clause 3.1: “Notwithstanding anything contained herein above, the Engineer is required to obtain specific written approval of the Employer before exercising the following specific authorities: - Determination of any additional payment in accordance with Sub- Clause 3.5 read with Sub-Clause 2.5 & 20.1; - Determination of any additional payment in accordance with Sub- Clause 3.5 read with Sub-Clause 4.12 & 20.1; |

|  | - Determination of Extension of Time for Completion in accordance with Sub-Clause 8.4 read with Sub-Clause 20.1; - Instructing the Contractor to suspend whole of the Works pursuant to Sub-Clause 8.8; - Issuing of Taking-Over Certificate pursuant to Clause 10; - Instructing or approving Variations pursuant to Sub-Clauses 13.1, 13.2 and 13.3 except in case of an emergency affecting the safety of life or of the works or of adjoining property, he may, without relieving the Contractor of any of his duties and responsibility under the Contract, instruct the Contractor to execute all such things as may, in the opinion of the Engineer, be necessary to abate or reduce the risk. In case the emergency mentioned above occurs on account of failure of Contractor, by way of not adhering to the sound industry practice or not taking adequate safety precautions, then no amounts shall be paid to the Contractor for attending to such emergencies. |
| --- | --- |
| 3.4 | DELETE “42 days” and REPLACE with “21 days”. |
| New clause 3.6 | Add the following new Sub-Clause 3.6: “The Engineer and the Contractor’s Representatives (Sub-Clause 1.1.2.5 and 4.3) shall attend progress review meetings called by the Employer to review the progress of the Works and other issues related with the Contract. The Engineer shall record the business of such meetings and supply copies of the record to the Employer, Contractor and other concerned persons/authorities. In the record of meetings, the responsibility for any actions to be taken shall be in accordance with the Contract.” |
| 4 | The Contractor |
| 4.1 | Add the following after second paragraph: Contractor shall design all temporary fixed, suspended platforms and fixtures , staging etc and get the same proof checked by third party. A check certificate need to be issued by the proof checking agency with respect to the strength and stability of the temporary platforms. INSERT at the end of Sub-Clause 4.1: Any documents other than Contractor’s Documents which are required to be submitted to the Engineer for approval under this Contract shall be submitted to the Engineer and the Engineer shall respond to the submittal within 14 days of receipt. If the document is returned to the Contractor marked as either “rejected” or “subject to comments”, then the Contractor shall resubmit the same to the Engineer within 7 days from receipt of the document, addressing the comments raised. The Engineer shall then respond within a further 7 days. For the avoidance of doubt, Contractor’s Documents shall be submitted for approval in accordance with Sub-Clause 5.2 [Contractor’s Documents]. |

| 4.2 | Delete the second paragraph of this Sub-Clause 4.2 and substitute with the following: “The Contractor shall deliver the Performance Security in the form of an unconditional Bank Guarantee in hard copy, to the Employer within 14 days after receiving the Letter of Acceptance and shall send a copy to the Engineer. The Bank Guarantee shall be issued by a Nationalized Bank or a Scheduled Commercial Bank having its branch in Mumbai and shall be in the format annexed to the Particular Conditions or in a similar format approved by the Employer.” Delete the word “or” at the end of sub-para (c) of fourth paragraph of Sub- Clause 4.2. Delete the fifth paragraph of Sub-Clause 4.2 in its entirety. INSERT at the end of Sub-Clause 4.2: Without limitation to the provisions of the rest of this Sub-Clause, whenever the Engineer determines an addition or a reduction to the Contract Price as a result of a change in cost and/or legislation or as a result of Variations amounting to more than 10 percent of the portion of the Contract Price payable in a specific currency, the Contractor shall at the Engineer's request promptly increase, or decrease, as the case may be, the value of the Performance Security in that currency by an equal percentage. |
| --- | --- |
| 4.3 | INSERT at the end of Sub-Clause 4.3: The Contractor's Representative and all these persons shall also be fluent in English and Hindi |
| 4.4 | Add the following paragraph at the end of the Sub-Clause 4.4: “Notwithstanding the provisions in sub paragraph (b) above, before giving consent for the employment of a proposed Subcontractor, the Engineer shall determine to its satisfaction that the Subcontractor has reasonable qualification and experience with reference to the Works proposed to be subcontracted and such determination shall be based on the documentary evidence submitted by the Contractor regarding experience, equipment and personnel of its proposed Subcontractor. |
| 4.8 | INSERT at the end of sub-paragraph (a) “and instructions from the Engineer” In sub-paragraph (c) after “obstruction” and before “so” INSERT “and keep Contractor’s Equipment in a state” Delete “and” from the end of sub-paragraph (d) and Replace “.” with “, and” at the end of sub-paragraph (e). Add a new sub-paragraph (f) at the end of sub-Clause 4.8: “(f) The Contractor shall also take adequate precautions to ensure that his operations do not present any hazard to the navigation and other operations in the sea around the Site.” |
| 4.10 | Add the following at the end of 1st paragraph of this Sub-Cause 4.10: “Accordingly, the Contractor shall have no claim in this regard.” |

|  | Delete the words “To the extent which was practicable (taking account of cost and time),” from the beginning of 1st sentence of 2nd paragraph of Sub- Clause 4.10 and start the sentence with “The” instead of “the”. Delete the words “To the same extent” from beginning of 2nd sentence of 2nd paragraph of Sub-Clause 4.10 and start the sentence with “The” instead of “the”. |
| --- | --- |
| 4.14 | INSERT after sub-paragraph (b): The Contractor shall be deemed to be fully cognizant that all construction activities (marine or land based) shall be performed within the confines and/or vicinity of a operational Port. Simultaneous activities (SIMOPS) are broadly defined as two or more activities performed by different groups that occur at the same time, which due to their proximity or interaction could have an adverse effect on each other. The Contractor shall initiate, prepare, discuss and agree an overall project SIMOPS plan with the Port Authority and the Employer to ensure that all potential SIMOPS conflicts are avoided. The SIMOPS plan shall focus on maritime operational activities within the Port and its immediate marine surroundings but will consider all construction related SIMOPS conflicts reasonably foreseeable by an experienced contractor. The SIMOPS plan shall take into consideration the following: - the Contractor shall be fully responsible for and hold ownership of the SIMOPS plan; - the SIMOPS plan shall be agreed with Port Authority and the Employer prior to the commencement of all construction activities and include all activities as can be reasonably foreseen; - unless specifically agreed with the Port Authority, all operational Port traffic shall have priority over all construction activities; - the harbour master of the Port shall issue final decision in case of dispute, and; - the Contractor shall make all reasonable efforts to minimize any SIMOPS interference. |
| 4.15 | Add the following paragraph at the end of Sub-Clause 4.15: “If any damage occurs to any bridge or road communicating with or on the routes to the Site arising from the transport of materials, equipment or plant, the Contractor shall notify the Engineer with a copy to the Employer, as soon as he becomes aware of such damage or as soon as he receives any claim from the Authority entitled to make such claim, whichever happens earlier. Where under any law or regulation the hauler of such materials, equipment or plant is required to indemnify the road Authority against damage, the Employer shall not be liable for any costs, charges or expenses in respect thereof or in relation there to.” |

| 4.19 | Delete the first paragraph and substitute: The Contractor shall, except as stated below, be responsible for the provision of all power, water and other services he may require for his construction activities and to the extent defined in the Specifications, for the tests. |
| --- | --- |
| 4.20 | Delete entire Sub-Clause 4.20 and replace with the following: “There shall be no free issue of any material by the Employer”. |
| 4.21 | Insert “and four (4) soft copies (read only)” between “copies” and “.” at the end of 1st sentence of 1st paragraph. Add the following at the end of the para: “(i) the Contractor’s forecast of the amounts expected to be spent on the Works performed within the next three months; The Contractor shall comply with the Employer’s requirements for work progress reporting, in the form(s) and format(s) as approved by the Engineer.” |
| 4.22 | Add the following after Sub-Clause (b): “(c) The Contractor shall comply with all security related requirements as determined by GPPL Security Officials and the Employer as provided in the Employer’s Requirements.” |
| 4.24 | Delete the words “to the Engineer” in line 1 and 4 of the second paragraph and replace by “to the Employer and to the Engineer”. Add the following new Sub-Clauses 4.25 and 4.30 after Sub-Clause 4.24: |
| New Sub-Clause 4.25 | Supplier Code of Conduct The Contractor shall, in performing the Contract, adhere to the Supplier Code of Conduct. In the event of any difference between the Contract and the Supplier Code of Conduct, the document providing for the stricter obligation or standard shall prevail. |
| New Sub-Clause 4.26 | Breach of Supplier Code of Conduct If the Contractor breaches the Supplier Code of Conduct or fails to collaborate with the Employer’s Auditor during an audit under Sub-Clause 4.28 [Compliance Auditing], and any such breach or failure has not been remedied to the satisfaction of the Employer within 28 days of receipt by the Contractor of a notice from the Employer requiring the Contractor to remedy the same (or such longer period as may be specified in the said notice), the Employer |

|  | shall be entitled to terminate the Contract in accordance with Sub-Clause 15.2 [Termination by Employer]. |
| --- | --- |
| New Sub-Clause 4.27 | Anti-Corruption and Export Control Compliance The Contractor shall, in performing the Contract, undertake and represent that it and all of its affiliates, directors, officers or subcontractors will comply in all material respects with all applicable laws, rules, regulations or similar instruments relating to anti-corruption, competition law and foreign trade controls (export controls and sanctions laws of the UN, the EU and US or other relevant regulator) and shall promptly notify the Employer in case it becomes aware or receives notice of a (alleged) violation of any applicable law. For the purposes of clarity: The Contractor shall not give, promise or attempt to give or approve the giving of anything of value to any person, for illegal purposes or for improperly obtaining or retaining business. The Contractor shall not deal, or cause the Employer to deal with, any person or entity in respect of transactions prohibited by foreign trade controls, except with Employer’s prior written consent; or which could damage the Employer’s commercial or other reputation interests, even if not in violation of any foreign trade controls. The Contractor has established processes, shall maintain policies and procedures to prevent violation of this Sub-Clause, and the Contractor shall maintain adequate records to verify and demonstrate its compliance with these provisions. The Contractor shall, upon written request from the Employer, confirm in writing its compliance with any of the provisions in this Sub-Clause 4.27 and provide any demonstration or proof of compliance as requested. If the Contractor breaches any of its obligations or representations in this clause, the Employer may terminate this Agreement with immediate effect without incurring any liability in accordance with Sub-Clause 15.2 [Termination by Employer]. The Contractor shall indemnify, defend and hold harmless the Employer from all fines, penalties and all associated expenses arising out of or resulting from a violation of any of its obligations under this Sub-Clause 4.27. |
| New Sub-Clause 4.28 | Compliance Auditing The Employer shall have the right to appoint an Employer’s Auditor to audit and verify all matters in connection with the Contractor’s compliance with the Contract. The Contractor shall cooperate with the Employer’s Auditor, provide access to all relevant sites and arrange interviews with all relevant personnel of the Contractor or any Subcontractor. If the Employer’s Auditor determines any concerns, the Contractor shall without any undue delay present the Employer with an improvement plan, which shall ensure that all such concerns are dealt with and remediated in a manner satisfactory to the Employer. |

| 5 | Nominated Subcontractors |
| --- | --- |
| 5.2 | In sub-paragraph (b) DELETE "the subcontract does not specify that the nominated Subcontractor shall" and REPLACE with "the nominated Subcontractor does not accept to". In sub-paragraph (c) DELETE "the subcontract does not specify" with "the nominated Subcontractor does not accept to enter into a contract which specifies". |
| 6 | Staff and Labour |
| 6.5 | Delete this entire clause and substitute with “The working hours are unrestricted and shall be 24 hours per day 7 days per week unless otherwise governed by Laws and Regulations in India”. |
| 6.7 | Add the following sentence at the end of the second paragraph: The Contractor shall comply with all statutory requirements, the Employer’s safety policy and any reasonable direction issued by the Employer’s safety department or authorised personnel of the Employer as may be issued from time to time. The cost of the provision of all safety precautions, equipment and clothing shall be borne by the Contractor. All works shall be carried out in a safe manner and free from any danger and shall comply with the relevant Laws regarding safety of the Works. All personnel who are in the work area and / or within the operations area of the Employer shall continually wear protection helmets and appropriate boots, and safety vests and belts when they are required by the Laws. Workers shall either wear high visibility vests or jackets or shall have appropriate high visibility adhesive stripes attached to their clothing. Life Jackets shall be worn by all staff working near and over water. The Contractor shall take all necessary precautions to protect the health and safety of persons where works may expose workmen and other persons on, or within the vicinity of the site, to conditions which are dangerous or potentially dangerous to health, including the noxious effects of dust, fumes, liquids, infection, fire, explosion, radiation, or other hazards. The Contractor shall strictly comply with “Tenderer’s Safety Guidelines” and “Consequence Management” (copy enclosed) and all other local regulations which may be in force from time to time. The Contractor shall strictly follow Port security rules and shall arrange and responsible for all securities of its Site, Works, workers, staffs, materials etc in port area. The Contractor shall responsible for taking necessary permission |

for the execution of Works from respective state/central government authority as required.

All workers and staffs of the Contractor and its Subcontractor shall wear safety boots with steel toes, safety helmets, visibility jackets, safety harnesses at the Site and also while working at heights. If any person of the Contractor fails to maintain PPE requirements. The Employer will impose a fine of INR 5000/- per occurrence at its sole discretion. Minimum PPE requirements for all personnel at the Site are helmet, high visibility jacket and Safety shoes with steel toe.

The working hour of individual persons/workers/staffs of the Contractor and its Subcontractor shall not be more than 8 hours per day at the Site. If Employer will impose a fine of INR 10000/- per incident in any noncompliance by the Contractor is noticed.

The Contractor shall strictly adhere the vehicle speed limit in the port area as under.

    - Outside Custom bonded area – 40 km per hour

    - Inside Custom bonded area – 30 km per hour

    - Jetty and container yard area – 20 km per hour

A fine of INR 5000 per incident will be imposed by the Employer on each no compliance by the Contractor. All the vehicles and equipment used by the Contractor shall comply all applicable rules & regulations.

Chewing and spitting of tobacco, gutka, mava, liquor or any such substances are strictly prohibited in Port area. The Contractor’s workers found chewing tobacco, will be sacked from the Site and a fine of INR 5000 will be imposed by the Employer.

Staff /workers of the Contractor and its Subcontractors on violations of port safety and security rules, shall be fined for

    - INR 30,000/- for each non-compliance report

    - INR 20,000/- for each near miss report

    - INR 10,000/- for each report on any other unsafe observation

All the amount towards fines stated above shall be deducted from the

Contractor’s Interim Payment Certificates.

Prior to commencement of the Works, the Contractor shall submit risk assessment of the Works & obtain approval from HSSE Department of the Employer. The Contractor shall

- organise and erect metal barricades around the work location for safety of workers and port operations traffic.

- arrange diversion as per site requirements including all required necessary arrangement like manpower, equipment, material etc.

- arrange and fix proper metal scaffolding for staging for the work as per APMT Guidelines and conforming to the latest IS standard.

- arrange adequate lighting arrangement, safety equipment, tools & tackles etc for working 24 hours by 07, or in night hour in shifts.

| 6.8 | INSERT at the end of Sub-Clause 6.8: A reasonable proportion of the Contractor's superintending staff shall be able to understand and communicate in English and Hindi. |
| --- | --- |
| 6.9 | Add the following paragraphs at the end of Sub-Clause 6.9: “If the key personnel named in the Contractor’s proposal could not be in place on the date as per the intent of the Sub-Clause 8.3 [Programme]; the Engineer may suspend that part of the Works until those key personnel, or a suitably replacement staff is provided. The replaced key personnel shall be equal to or better than the original proposed key personnel in terms of experience and qualification. Consent of such replaced personnel shall be obtained from the Engineer by the Contractor, before putting such replaced personnel in place. Any cost and time effect of such suspension of part of the Works shall be borne by the Contractor.” |
| New Sub-Clause 6.12 | Add the following new Sub-Clauses 6.12: The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour from sources within India. |
| New Sub-Clause 6.13 | Add the following new Sub-Clauses 6.13: The Contractor may import any personnel who are necessary for the execution of the Works. The Contractor must ensure that these personnel are provided with the required residence visas and work permits in India & comply the all Indian Law. The Contractor shall be responsible for the repatriation Contractor's non- local Personnel. In the event of the death in the Country of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial. |
| 6.14 | Add the following new Sub-Clauses 6.14: The Contractor shall at all times take the necessary precautions to protect all staff and labour employed on the Site from insect and pest nuisance, and to reduce their danger to health. The Contractor shall provide suitable prophylactics for the Contractor's Personnel and shall comply with all the regulations of the local health authorities, including use of appropriate insecticide. |
| 6.15 | Add the following new Sub-Clauses 6.15: |

|  | The Contractor shall not, in accordance with the Laws of the Country, import, sell, give, barter or otherwise dispose of any alcoholic liquor or drugs, or permit or allow importation, sale, gift, barter or disposal by Contractor's Personnel. |
| --- | --- |
| 6.16 | Add the following new Sub-Clauses 6.16: The Contractor shall not give, barter or otherwise dispose of to any person, any arms or ammunition of any kind, or allow Contractor's Personnel to do so. |
| 6.17 | Add the following new Sub-Clauses 6.17: The Contractor shall respect the Country's recognised festivals, days of rest and religious or other customs. |
| 6.18 | Add the following new Sub-Clauses 6.18: The Contractor shall arrange for the provision of a sufficient supply of suitable food as may be stated in the Specification at reasonable prices for the Contractor's Personnel for the purposes of or in connection with the Contract. |
| 6.19 | Add the following new Sub-Clauses 6.19: The Contractor shall, having regard to local conditions, provide on Site an adequate supply of drinking and other water for the use of the Contractor's Personnel. |
| 6.20 | Add the following new Sub-Clauses 6.20: The Contractor shall be responsible, to the extent required by local regulations, for making any funeral arrangements for any of his local employees who may die while engaged under the Works. |
| 6.21 | Add the following new Sub-Clauses 6.21: The Contractor shall not employ "forced or compulsory labour" in any form. "Forced or compulsory labour" consists of all work or service, not voluntarily performed, that is extracted from an individual under threat of force or penalty. |
| 6.22 | Add the following new Sub-Clauses 6.22: |

|  | The Contractor shall not employ any child to perform any work that is economically exploitative, or is likely to be hazardous to, or to interfere with, the child's education, or to be harmful to the child's health or physical, mental, spiritual, moral, or social development. |
| --- | --- |
| 6.23 | Add the following new Sub-Clauses 6.23: The Contractor shall keep complete and accurate records of the employment of labour at the Site. The records shall include the names, ages, genders, hours worked, and wages paid to all workers. These records shall be summarised on a monthly basis and shall be available for inspection by the Engineer, during normal working hours. These records shall be included in the details to be submitted by the Contractor under Sub-Clause 6.10 Records of Contractor's Personnel and Equipment. The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour with appropriate qualifications and expertise from sources within the Country. |
| 7 | Plant, Materials and Workmanship |
| 7.4 | Add the following after Sub-Clause 7.4: “The Contractor shall not be released from any liability or obligation under the Contract by reason of any such inspection or testing or witnessing of testing, or by the submission of reports of inspection or testing to the Engineer.” |
| 8 | Commencement, Delays and Suspension |
| 8.2 | Insert “stated in the Appendix to Tender” between “Time for Completion” and “for the Works” in the 1st paragraph. |
| 8.3 | Delete the first paragraph and substitute: |

|  | The Contractor shall submit a detailed time programme to the Engineer within 28 days after receiving the notice under Sub-Clause 8.1 (Commencement of Works). The Contractor shall also submit a revised programme whenever the previous programme is inconsistent with actual progress or with the Contractor's obligations including whenever the Engineer has granted an extension of time to complete the Works under Sub-Clause 3.5 and 20.1. Add the following paragraphs at the end of the Sub-Clause: For the avoidance of doubt, the Contractor shall only be entitled to an extension of Time for Completion provided it has demonstrated and made all reasonable efforts to mitigate any delay. Any failure by the Employer to rely upon any antecedent breach of a condition precedent will not amount to a waiver by the Employer of its rights in this respect. Further, where more than one event causes concurrent delays and the cause of at least one of those events, but not all of them, is a cause of delay which would not entitle the Contractor to an extension of time then to the extent that the delays are concurrent, the Contractor shall not be entitled to an extension of time. |
| --- | --- |
| 8.4 | Add the following between “Sections]” and “is” in the 3rd line of 1st paragraph of Sub-Clause 8.4: “or for achievement of Milestone(s)” In sub-paragraph (d) after “epidemic” INSERT “, pandemic”. INSERT at the end of Sub-Clause 8.4: For the avoidance of doubt, the Contractor shall only be entitled to an extension of Time for Completion provided it has demonstrated and made all reasonable efforts to mitigate any delay. |
| 8.7 | Delete Sub-Clause 8.7 and substitute with the following: If the Contractor fails to comply with Sub-Clause 8.2 [Time for Completion], the Contractor shall subject to Sub-Clause 2.5 [Employer’s Claims] pay delay damages to the Employer for this default. Delay damages, for failure to complete the Whole of the Works and /or Section(s), (if any) within the Time for Completion shall be the sum stated in the Appendix to Tender, which shall be which shall be deducted from the Contractor’s Interim Payment Certificate(s) for every day which shall elapse between the relevant Time for Completion and the date stated in the Taking- Over Certificate. Delay damages, for failure to achieve the Milestones in accordance with the Time for Completion set forth in Sub-Clause 8.2 [Time for Completion] shall be the sum stated in the Appendix to Tender, which shall be deducted from |

|  | the Contractor’s Interim Payment Certificate(s) for every day which shall elapse between the relevant Time for Completion until the Milestone has been achieved. For the avoidance of doubt, it is agreed between the Parties that delay damages for two or more Milestones shall run concurrently, if applicable. The Employer may, without prejudice to any other method of recovery, deduct the amount of delay damages from any sum due, or to become due to the Contractor or from the Performance Security of the Contractor or any other amounts of the Contractor due from the Employer. Notwithstanding the above, the total amount of damages for failure to comply Sub-Clause 8.2 [Time for Completion] shall not exceed the maximum amount of delay damages (if any) stated in the Appendix to Tender. These delay damages shall be the only damages due from the Contractor for failure to comply Sub-Clause 8.2 [Time for Completion] other than in the event of termination under Sub-Clause 15.2 [Termination by Employer] prior to completion of the Works. These damages shall not relieve the Contractor from his obligation to complete the Works, or from any other duties, obligations or responsibilities which he may have under the Contract. It is also agreed that recovery of damages under this Sub-Clause shall be without prejudice to the rights of the Employer under this Contract including the right of Termination thereof. |
| --- | --- |
| 8.8 | INSERT at the end of Sub-Clause 8.8: Throughout any suspension, the Contractor shall maintain its staff and labour resources ready to recommence work, unless agreed otherwise with the Engineer. The Contractor shall notify the Engineer of details of any of its staff and labour that it proposes to redeploy to other projects and the Engineer may instruct the Contractor not to so redeploy any staff or labour it considers to be key to the project. |
| New Sub-Clause 8.13 | Other contractors The Contractor shall take due account of the presence of other contractors, employed by the Employer or by other parties, who may be working immediately adjacent to or overlapping with the Site during part or all of the Contract period. The Contractor shall be deemed to have taken all reasonable steps to avoid delay and interference with or from these other contractors and shall be expected to cooperate fully with these contractors wherever possible. |
| 9 | Test on Completion |
| 9.1 | Delete the first paragraph and substitute: |

|  | The Contractor shall carry out the Tests on Completion required by the Specification in accordance with this Clause and Sub-Clause 7.4 [Testing], after providing the documents in accordance with Sub-paragraph (d) of Sub- Clause 4.1 [Contractor's General Obligations]. |
| --- | --- |
| 10 | Employer’s Taking Over |
| 10.2 | Delete the words “plus reasonable profit” in 4th/5th line and delete “and profit” at the end of 4th paragraph of Sub-Clause 10.2. |
| 11 | Defects Liability |
| 11.1 | Add the words “defined in Appendix to the Tender” after “Defects Notification Period” in the first paragraph. |
| 12 | Measurement and Evaluation |
| 12.3 | Add the following paragraph at the end of the Sub-Clause: The Employer reserves the right to reduce or delete certain aspects of the Works during the construction period by informing the Engineer and the Contractor in writing of the proposed changes. Calculation of the amended value of the Works shall be based on measured work at rates defined in the Bill of Quantities. |
| 13 | Variations and Adjustments |
| 13.5 | Delete this Sub-Clause in its entirety. |
| 13.8 | Replace the Sub-clause with the following: “The Contractor shall not be entitled to claim additional payment due to rises or falls in the cost of labour, Goods and any other inputs to the Works.”. |
| 14 | Contract Price and Payment |
| 14.1 | Add the following after the last paragraph: The Contract Price includes all duties, taxes (excluding GST), Stamp Duty, Labour Cess, BoCW, Royalties, premiums for various insurances, licenses and fees that may be levied in accordance with the Laws and regulations in force as on the Base Date on the Contractor's Equipment, Plant, Materials and supplies acquired for the purpose of the Contract and on the services performed under the Contract. The GST shall be paid extra as per the prevailing rates. Nothing in the Contract shall relieve the Contractor from its responsibility to pay any tax including any tax that may be levied in India on profits made by it in respect of the Contract. |
| 14.2 | Delete the last sentence of the third paragraph and substitute: |

|  | This guarantee shall be in the form annexed as Annex D issued by a reputable national/schedule bank to be approved in advance in writing by the Employer. |
| --- | --- |
| 14.16 | Add the following new Sub-Clauses after Sub-Clause 14.15: Add the new Sub-Clause 14.16: The Contractor’s rates and prices defined in the Contract Price which shall include but not limited to , all freight and insurance charges, harbour dues, pilotage, wharfage, port rates, custom duties, tolls landing charges, octroi and all other all duties, taxes & dues in respect of plant and equipment, ancillaries, spares, lubricants, etc imported into India and brought into Gujarat in connection with the Works. This is excluding any port charges which will otherwise be levied by the Gujarat Pipavav Port Limited. |
| 14.17 | Add the new Sub-Clause 14.17: The Contract Price shall be exclusive of Gujarat State Service Tax, but include all customs duties, import duties, business taxes, and income and other taxes duties, levies, royalties, cess, TCS, etc. that may be levied in accordance with the laws and regulations in being on the date 28 days prior to the latest date for submission of bids in the Employer's country on the Contractor's Equipment, and supplies (temporary and consumable) acquired for the purpose of the Contract and on the services performed under the Contract. Nothing in the Contract shall relieve the Contractor from his responsibility to pay any tax that may be levied in the Employer's country on profits made by him in respect of the Contract. |
| 14.18 | Add the new Sub-Clause 14.18: The Contractor's Personnel shall be liable to pay personal income taxes in the Employer's country in respect of such of their salaries and wages as are chargeable under the laws and regulations for the time being in force, and the Contractor shall perform such duties in regard to such deductions thereof as may be imposed on him by such Laws and regulations. |
| 15 | Termination by Employer |
| 15.2 | INSERT new sub-paragraphs (g), (h) and (i) as follows: - fails to comply with Sub-Clause 4.8 [Safety Procedures], - fails to comply with a notice served by the Employer pursuant to Sub- Clause 4.26 [Breach of Supplier Code of Conduct], or - fails to comply with Sub-Clause 4.27 [Anti-Corruption and Export Control Compliance], |

|  | DELETE in the third paragraph “in the case of sub-paragraph (e) or (f)” and REPLACE by “in the case of sub-paragraph (e), (f), (g), (h) or (i)”. At the end of Paragraph, add the words “The Contractor shall promptly remove all of the Contractor’s Equipment from the Site.” |
| --- | --- |
| 15.5 | Add the following paragraphs at the end of the Sub-Clause: If the Employer determines that the Contractor has engaged in corrupt, fraudulent, collusive or coercive practices, in competing for or in executing the Contract, then the Employer may, after giving 14 days' notice to the Contractor, terminate the Contractor's employment under the Contract and expel him from the Site, and the provisions of Clause 15 shall apply as if such expulsion had been made under Sub-Clause 15.2 (Termination by Employer). Should any employee of the Contractor be determined to have engaged in corrupt, fraudulent or coercive practice during the execution of the Works then that employee should be removed in accordance with Sub- Clause 6.9 [Contractor's Personnel]. |
| 16 | Suspension and Termination by Contractor |
| 16.1 | Delete the words “to the Engineer” in line 3 of the fourth paragraph and replace by “to the Employer and to the Engineer”. DELETE in the first paragraph “or the Employer fails to comply with Sub- Clause 2.4 [Employer's Financial Arrangements]”. Delete the 2nd paragraph of Sub-Clause 16.1 in entirety. |
| 16.2 | DELETE sub-paragraph (a) and (g). Delete the words “or Sub-Clause 1.7 [Assignment]” at the end of sub- paragraph (e) of Sub-Clause 16.2 |
| 16.4 | In sub-paragraph (c) DELETE “loss of profit or other loss or”. |
| 17 | Risk and Responsibility |
| 17.1 | INSERT sub-paragraph (c) as follows: (c) and, any breach by the Contractor of its obligations under Sub-Clauses 4.25 [Supplier Code of Conduct], 4.26 [Breach of Supplier Code of Conduct] or 4.27 [Export Control]. |
| 17.3 | INSERT at the end of the first sentence: “insofar as they directly affect the execution of the Works in the Country”. |

| 17.4 | Delete the words “to the Engineer” in line 3 of the first paragraph and line 2 of the second paragraph and replace by “to the Employer and to the Engineer”. |
| --- | --- |
| 17.6 | In the first line of the second paragraph, insert “cumulative” after the word “total”. At the end of the second paragraph, replace the words “the sum stated in the Particular Conditions or (if a sum is not so stated) the Accepted Contract Amount” with the words “ten percent (10%) of the Contract Price, including without limitation Delay Damages. The foregoing is without prejudice to the right of Contractor to avail itself of the benefits of the Convention on Limitation of Liability for Maritime Claims”. INSERT at the end of Sub-Clause 17.6: This Sub-Clause shall not apply to a breach by the Contractor of any of Sub- Clauses 1.13 [Compliance with Laws], 4.25 [Supplier Code of Conduct], 4.26 [Breach of Supplier Code of Conduct] or 4.27 [Anti-Corruption and Export Control Compliance]. |
| 18 | Insurance |
| 18.2 | DELETE the entire Sub-Clause and SUBSTITUTE: The insuring Party shall insure the Works, Plant, Materials and Contractor’s Documents for not less than the full Accepted Contract Amount and including a provision for the costs of demolition, removal of debris, professional fees and profit. This insurance shall be effective from the Commencement Date until the date of issue of the Taking-Over Certificate for the Works. The insuring Party shall maintain this insurance to provide cover until the date of issue of the Performance Certificate, for loss or damage for which the Contractor is liable arising from a cause occurring on the Site, including storage, disposal, borrow pit and any other working areas, after the Commencement Date and prior to the issue of the Taking-Over Certificate, and for loss or damage caused by the Contractor on the Site, including storage, disposal, borrow pit and any other working areas, in the course of any other operations (including those under Clause 11 [Defects Liability] and Clause 12 [Tests after Completion]). The insuring Party shall insure the Contractor's Equipment for not less than the full replacement value, including delivery to Site. For each item of Contractor's Equipment, the insurance shall be effective while it is being transported to the Site and until it is no longer required as Contractor's Equipment. If the Contractor’s Equipment includes vessels, items of floating equipment or watercraft, the insuring Party shall effect, or require that the owners effect, and maintain charterer’s liability insurance, customary material damage, hull and machinery insurance with limits of liability of the full replacement cost of the vessel, items of floating equipment or watercraft, and protection and indemnity insurance for a limit of not less than INR 20 crores for any one occurrence or series of occurrences arising out of one event. |

|  | Unless otherwise stated in the Particular Conditions, insurances under this Sub-Clause: - in relation to the Works, Plant, Materials and Contractor’s Documents located on the Site, including storage, disposal, borrow pit and any other working areas, shall be effected and maintained by the Employer as insuring Party; - in relation to the Plant, Materials and Contractor’s Documents located off the Site, including in the course of transit to and from the Site within the Country, shall be effected and maintained by the Employer as insuring Party. For transit to and from locations outside the Country, the Contractor shall be the insuring Party, naming the Employer and Lenders as co-insured. In the event of transits of any Plants and Materials critical to the timely completion of the Project, the Employer reserves the right to be the insuring Party; - in relation to the Contractor's Equipment, shall be effected and maintained by the Contractor as insuring Party; and - coverage for the Works, Plant, Materials and Contractor’s Documents shall be in the joint names of the Parties, who shall be jointly entitled to receive payments from the insurers, payments being held or allocated between the Parties for the sole purpose of rectifying the loss or damage. The Contractor shall bear the cost of any deductibles applying to any insurance claims made on the Employer’s insurance policies which arise from occurrences or events for which the Contractor is responsible under the contract or otherwise and shall, in making any claim, comply with the Employer’s insurance claims procedure. The Contractor shall make all of his Subcontractors and suppliers aware of this obligation. All insurances to be effected by the Employer under this contract shall be with insurers and on terms to be approved solely by the Employer. The Contractor shall be deemed to have satisfied himself and shall cause all of his Subcontractors and suppliers to satisfy themselves with regard to the extent of cover provided under the policies of insurance effected by the Employer. The Contractor is deemed to have read and understood all the terms of the insurance provided by the Employer. If, in the Contractor’s opinion, the amounts and/or risks insured are insufficient to cover the Contractor’s duties, obligations and liabilities under this contract or otherwise, the Contractor may effect such further insurance at Contractor’s own cost. The Contractor shall for himself and on behalf of all his Subcontractors and suppliers accept the insurance policies effected by the Employer as if they had been arranged by him directly and shall with all due diligence observe and fulfil and procure that his Subcontractors and suppliers observe and fulfil the terms contained in the said policies. Parties hereby agree that in any type of insurance as herein provided, the insurance institution shall waive its right to subrogate against the Employer in connection with the insurance. |
| --- | --- |
| 18.3 | DELETE the entire sub-paragraphs (c) and (d) up to the end of the Sub- Clause. |

| 18.4 | Delete the words “The Contractor” in line 1 of the first paragraph and replace by “Pursuant to Workers Compensation legislation or any other law amending or replacing such legislation, the Contractor”. Delete the second paragraph and substitute: The insurance shall cover the Employer and the Engineer against liability for claims, damages, losses and expenses (including legal fees and expenses) arising from injury, sickness, disease or death of any person employed by the Contractor or any other of the Contractor's Personnel, except this insurance may exclude losses and claims to the extent that they arise from any act or neglect of the Employer or the Employer's Personnel. Add the following paragraph at the end of the Sub-Clause: The Contractor shall not be required to take out any Workmen's Compensation Insurance Policy if the workers employed in the Works are eligible for coverage under any employee’s social security laws and regulations that may be in place and are so covered. The Contractor shall register his employees and contribute under the relevant social security scheme in the places where the scheme is implemented and comply with the provisions of the relevant laws and regulations. The Contractor shall submit the code number and insurance numbers of all the workers on site to the Engineer for checking. Add the following new Sub-Clauses 18.5 to 18.7 after Sub-Clause 18.4: |
| --- | --- |
| New Sub-Clause 18.5 | Additional Insurances The Contractor shall effect and maintain, in full force until the works are delivered to Employer, subject to the terms set forth herein, the following insurances with an “A” insurance company, incorporated in the Country, satisfactory to Employer, duly authorized to do business in the Country: - Automobile liability Insurance against claims by third parties in respect of bodily injury (including death) and property damage arising out of and in connection with the use of all owned, leased, non-owned and hired vehicles used in connection with the performance of the Works in accordance with statutory obligations and for the following minimum limits: - in respect of bodily injury (including death), on an unlimited basis; and - in respect of property damage, on a INR 2 crores any one occurrence unlimited as to the number of claims basis. - Civil liability caused by cargo in transit including hazardous cargo As regards to cargo vehicles that transport raw materials, equipment and/or materials used in the construction of the Works, same shall have |

|  | the coverage of civil liability for damages related to the cargo, and if required by the scope of the construction works as provided in these Conditions, it shall have coverage of civil liability for any for hazardous cargo. This insurance shall be in an amount not less than the responsibility limits of INR 2 crores per occurrence or arising from same event and shall include a contractual liability insurance applicable to Contractor’s o obligations. |
| --- | --- |
| 18.6 | Add the following new Sub-Clauses 18.6 If the Contractor receives instructions from the Employer to insure against War Risk, such insurance if available shall be effected, at the cost of the Employer, with an Insurance Company acceptable to the Employer and shall be in the joint names of the Contractor and the Employer. |
| 20 | Claims, Disputes and Arbitration |
| 20.1 | INSERT after sub-paragraph (c): If the Contractor fails to submit within the 42day period described above, a detailed claim including supporting particulars of the basis of the claim and of the extension of time and/or additional payment claimed, then the Time for Completion shall not be extended, the Contractor shall not be entitled to additional payment and the Employer shall be discharged from all liability in connection with the claim. INSERT before the final paragraph: If the Engineer does not respond within such period, the Employer shall instruct the Engineer to do so, upon failure of which within the timeframe set by the Employer after consultation with the Contractor, the claim shall be deemed rejected by the Engineer and either Party may refer to the Dispute Adjudication Board in accordance with Sub-Clause 20.4 [Obtaining Dispute Adjudication Board's Decision]. Add the following paragraph at the end of the Sub-Clause: Within the above defined period of 42 days, the Engineer shall proceed in accordance with Sub-Clause 3.5 [Determinations] to agree to determine (i) the extension (if any) of the Time for Completion (before or after its expiry) in accordance with Sub-Clause 8.4 [Extension of Time for Completion], and/or (ii) the additional payment (if any) to which the Contractor is entitled under the Contract. Delete the second last paragraph of the Sub-Clause and substitute: |

|  | If the Engineer does not respond within the timeframe defined in this Clause, either Party may consider that the claim is rejected by the Engineer and any of the Parties may refer to the Dispute Board in accordance with Sub-Clause 20.4 [Obtaining Dispute Board's Decision]. |
| --- | --- |
| 20.6 | INSERT a new sub-paragraph (d): - and, the arbitration shall take place in Ahmedabad, Gujarat Add the following paragraph at the end of the Sub-Clause: - The law governing this Clause 20 will be the governing law of the Contract as stated in the Appendix to Tender. |
| 20.7 | Add the following paragraph at the end of the Sub-Clause: In the event that a Party fails to comply with a decision of the DAB, then the other Party may, without prejudice to any other rights it may have, refer the failure itself to arbitration under Sub-Clause 20.4 [Obtaining Dispute Adjudication Board's Decision] and Sub-Clause 20.5 [Amicable Settlement] shall not apply to this reference. |
| 21 | Hire Purchase for Contractor’s Equipment |
| 21.1 | With a view to securing, in the event of termination of the agreement of hire purchase, against the repossession by the owner, of any Contractor’s Equipment held by the Contractor, for the purpose of executing the Works, under an agreement for hire purchase, the Employer shall be entitled to pay to such owner the amount of any due installments or other such sums payable under any such agreement for hire purchase. The Contractor shall not bring on to the Site any Contractor's Equipment held under an agreement for hire purchase unless there is an agreement which contains a provision that the owner thereof will, on request in writing made by the Employer and accept payment from the Employer of due installments or other such sums payable under the agreement and transfer the benefit of the hire purchase agreement from the Contractor to the Employer on the same terms and conditions except that the Employer shall be entitled to use the Equipment or permit the use thereof by any Contractor employed by him for the purpose of executing and completing the Works and remedying any defects therein. |
| 21.2 | In the event of the Employer entering into any agreement for the hire of Contractor's Equipment pursuant to Sub-Clause 21.1 and 21.2, all sums properly paid by the Employer under the provisions of any such agreement and all costs incurred by him (including stamp duties) in entering into such agreement shall be deemed to be part of the cost of executing and completing the Works and the remedying of any defects therein. |

| 21.3 | The Contractor shall in respect of any item of Contractor's Equipment held by him under any agreement for hire or hire purchase thereof notify to the Engineer in writing the name and address of the owner thereof or the name and address of the vendor named in such agreement for hire or hire purchase and shall certify that such agreement contains a provision in accordance with Clause 21. A certified copy of the agreement shall be supplied to the Engineer when required. |
| --- | --- |
| 21.4 | The Contractor shall, where entering into any sub-contract for the execution of any part of the Works, incorporate in such Subcontracts (by reference or otherwise) the provisions of this Clause in relation to Contractor's Equipment, Temporary Works, Goods or materials brought onto the Site by the Subcontractor. Annexures to Particular Conditions of Contract |

  - Annex A: Form of Parent Company Guarantee

  - Annex B: Form of Tender Security

  - Annex C: Form of Performance Security

  - Annex D: Form of Advance Payment Guarantee

  - Annex E: Form of Dispute Adjudication Board Agreement

  - Annex F: Form of Letter of Tender

  - Annex G: Supplier Code of Conduct