Appendix to Tender

| Item | Sub-Clause | Data |
| --- | --- | --- |
| Employer's name and address | 1.1.2.2 & 1.3 | Gujarat Pipavav Port Ltd Post Rampara-2 Via Rajula, Distt Amreli Pipavav Port – 365 560 Gujarat (India) T: +91 (0)2794-286001 F: +91 (0)2794-286312 |
| Contractor's name and address | 1.1.2.3 & 1.3 | [ To be inserted xxxx…] |
| Engineer's name and address | 1.1.2.4 & 1.3 | Gujarat Pipavav Port Ltd Post Rampara-2 Via Rajula, Distt Amreli Pipavav Port – 365 560 Gujarat (India) T: +91 (0)2794-286001 F: +91 (0)2794-286312 |
| Time for Completion of the Works | 1.1.3.3 & 8.2 | Refer Time for Completion of Milestones as stated in this Appendix herein below. |
| Defects Notification Period | 1.1.3.7 & 11.1 | 365 Days from the date of Taking Over Certificate for respective Milestones |
| Electronic transmission systems | 1.3 | Email |
| Governing Law | 1.4 | Laws of Republic of India |
| Ruling language | 1.4 | English |
| Language for communications | 1.4 | English |
| Time for access to the Site | 2.1 | Within zero (0) days from the Commencement Date |
| Amount of Performance Security | 4.2 | 10% of the Accepted Contract Amount, in the currencies and proportions in which the Contract Price is payable |
| Normal working hours | 6.5 | Unrestricted, 24 hours a day, 7 days a week, but subject to applicable Laws, |
| Delay Damages for the Works | 8.7 & 14.15(b) | Refer details for Milestone as stated in this Appendix herein below. |
| Maximum amount of delay damages | 8.7 | 10% of the final Contract Price |
| Percentage for adjustment of Provisional Sums | 13.5(b) | Not applicable |
| Adjustments for Changes in Cost | 13.8 | Not applicable |
| Total advance payment | 14.2 | 10% of the Accepted Contract Amount |
| Number and timing of instalments | 14.2 | 2 instalments: - 5% of Accepted Contract Amount as first advance payment on submission of Performance Security |

|  |  | - 5% of Accepted Contract Amount after completion of office set up, labour shelters, fabrication yard and erection of all site facilities for the Contractor (i.e. ready to occupy) The Advance Payment shall be released on submission of unconditional Bank Guarantee for an amount equivalent to one hundred (100) percent of the amount of the advance payment requested by the Contractor. The bank Guarantee shall be issued by a nationalized bank or scheduled commercial bank permitted to carry out business in India by the Reserve Bank of India. |
| --- | --- | --- |
| Currencies and proportions | 14.2 | 100% in Indian Rupees |
| Start repayment of advance payment | 14.2(a) | First Interim Payment Certificate |
| Repayment amortization of advance payment | 14.2(b) | 10% |
| Percentage of retention | 14.3 | 10% cash retention (no bond) |
| Limit of Retention Money | 14.3 | 10% of the Contract Price |
| If Sub-Clause 14.5 applies: |  |  |
| Plant and Materials for payment when shipped en route to the Site | 14.5(b) | Not applicable |
| Plant and Materials for payment when delivered to the Site | 14.5(c) | Not applicable |
| Minimum amount of Interim Payment Certificates | 14.6 | 5% of the Accepted Contract Amount |
| Currency of payment | 14.15 | INR (Indian Rupees) |
| Insuring Party Periods for submission of insurance: - evidence of insurance - relevant policies | 18.1 18.1 18.1 | The Insuring Party shall be the Contractor. Insurances shall be affected with an insurance company approved by the Employer and on approved terms. 21 days 30 days |
| Maximum amount of deductibles for insurance of the Contractor’s risks | 18.2(d) | Nil |
| Minimum amount of third party insurance | 18.3 | INR 10,00,00,000 (INR Ten Crores) for any one occurrence or series of events arising from one occurrence, with no aggregate limit. |
| Date by which the DAB shall be appointed | 20.2 | within 28 days after Commencement Date |
| The DAB shall be | 20.2 | A DAB of three Members |
| Appointment (if not agreed) to be made by | 20.3 | The President of FIDIC or a person appointed by the President |

Definition of Sections:

| Description (Sub-Clause 1.1.5.6) |  | Time for Completion from Commencement Date (Sub-Clause 1.1.3.3) |  | Delay Damages (Sub-Clause 8.7) |  | Maximum Amount of Delay Damages (Sub-Clause 8.7) |
| --- | --- | --- | --- | --- | --- | --- |
| Completion of Road including Electrical works |  | 180 days including mobilization |  | 0.1% of the final Contract Price per day plus taxes, |  | 10% of the Contract Price |

Initials of signatory of Tender………………………………………………………………………………………..……………………